## 产品
PROJECT VISION
PROJECT | Name : | 学习牧场
Vision:
标题 | 用户故事
登陆 | 作为一个用户，我希望有安全的登陆功能，以便可以保护我的账户信息安全
木棚 | 作为一个用户，我希望在游戏中有木棚，以便我的宠物可以有可观的生存环境
商城 | 作为一个用户，我希望在游戏中有商城，以便我可以购买物品
仓库 | 作为一个用户，我希望在游戏中有仓库，以便我可以查看我的物品、出售仓库内的物品
设置 | 作为一个用户，我希望可以有设置功能，以便我可以管理我的个人信息
工具 | 作为一个用户，我希望可以有工具功能，以便我可以利用工具拍蚊子、铲屎、收获
活动 | 作为一个运营商，我希望可以有一个活动列表并且通知功能，以便可以让用户查看所有活动并且提醒用户有新的活动
答题 | 作为一个运营商，我希望可以有一个答题功能，以便可以让用户通过答题获得饲料，提高学习兴趣。
游戏好友 | 作为一个用户，我希望可以有一个游戏好友功能，以便我可以在游戏里中广泛交友
Note on D3: Luc Segers: Insert the name of the project
Note on D4: Luc Segers: Insert the descript of the Vision

## 第一次迭代
冲刺号 | 标题 | 用户故事 | 标题 | 用户故事分解 | 任务 | 责任人 | 优先级 | 预估(h) | Status
1 | 登录 | 作为一个用户，我希望有安全的登陆功能，以便可以保护我的账户信息安全 | 账号登陆 | 作为一个用户，我希望有安全的账号登陆功能，以便可以保护我的账户信息安全 | 编写账户登录页面及后台sql | 张帅华 | 95 | 3 | Done
|  |  | qq登陆 | 作为一个用户，我希望有安全的qq登陆功能，以便我可以快速登录 | 调用qq登录接口 | 张帅华 | 91 | 2 | Done
|  |  | 微信登陆 | 作为一个用户，我希望有安全的微信登陆功能，以便我可以快速登录 | 调用微信登录接口 | 张帅华 | 90 | 2 | Done
2 | 木棚 | 作为一个用户，我希望在游戏中有木棚，以便我的宠物可以有可观的生存环境 | 木棚界面 | 作为一个用户，我希望可以有可观的木棚界面，以便有良好的用户体验 | 编写带有动画功能的木棚界面 | 李帅 | 85 | 5 | Done
|  |  | 扩建木棚 | 作为一个用户，我希望可以扩建木棚，以便有更多的木棚可以居住 | 编写扩建木棚的"木牌"，创建新的木棚， | 李帅 | 83 | 1 | Done
|  |  | 升级木棚 | 作为一个用户，我希望可以升级木棚，以便木棚更大更美观，增强游戏体验 | 编写升级木棚的"木牌"，升级新的木棚， | 李帅 | 80 | 2 | Done
3 | 商城 | 作为一个用户，我希望在游戏中有商城，以便我可以购买物品 | 购买幼崽 | 作为一个用户，我希望在游戏里中有能够购买幼崽，以便我可以拥有更多的动物 | 编写幼崽出售界面布局以及后台管理 | 杨锡涛 | 75 | 5 | Done
|  |  | 购买装饰 | 作为一个用户，我希望在游戏里能够购买木棚的装饰，以便我可以随意的装饰自己的木棚 | 编写装饰出售界面布局以及后台管理 | 杨锡涛 | 73 | 2 | Done
|  |  | 购买管理员 | 作为一个用户，我希望在游戏里能够购买管理员，以便我可以通过管理员看守牧场 | 编写管理员出售界面布局以及后台管理 | 杨锡涛 | 70 | 2 | Done
Note on A1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on B1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on C1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable

## 第二次迭代
冲刺号 | 标题 | 用户故事 | 标题 | 用户故事分解 | 任务 | 责任人 | 优先级 | 预估(h) | Status
4 | 仓库 | 作为一个用户，我希望在游戏中有仓库，以便我可以查看我的物品、出售仓库内的物品 | 存储道具、幼崽、食物，装饰等。 | 作为一个用户，我希望在游戏里有仓库系统，以便我可以通过仓库存储购买的道具、幼崽、装饰品等 | 编写仓库布局界面以及后台管理 | 景光赞 | 68 | 5 | Done
|  |  | 出售已有的管理员、幼崽、食物，装饰等。 | 作为一个用户，我希望在游戏中有出售功能，以便我可以通过仓库卖掉不需要的管理员、幼崽、食物，装饰等 | 编写仓库出售功能以及后台管理 | 景光赞 | 66 | 2 | Done
5 | 设置 | 作为一个用户，我希望可以有设置功能，以便我可以管理我的个人信息 | 修改昵称 | 作为一个用户，我希望在游戏里有修改昵称的功能，以便我可以随时修改自己的昵称 | 编写修改昵称的界面并实现功能 | 张帅华 | 65 | 1 | Done
|  |  | 修改年级 | 作为一个用户，我希望在游戏里有修改年级的功能，以便我可以根据自己年级做答题系统对应年级难度的题 | 编写修改年级的界面并实现功能 | 张帅华 | 64 | 1 | Done
|  |  | 修改密码 | 作为一个用户，我希望在游戏里有修改密码的功能，以便我可以对账号密码随时修改 | 编写修改密码的界面并实现功能 | 张帅华 | 63 | 1 | Done
|  |  | 修改头像 | 作为一个用户，我希望在游戏里有修改头像的功能，以便我可以随时选择喜欢的头像 | 编写修改头像的界面并实现功能 | 张帅华 | 62 | 2 | Done
|  |  | 绑定邮箱 | 作为一个用户，我希望在游戏里有绑定邮箱的功能，以便我可以通过邮箱找回密码 | 编写绑定邮箱的界面并实现功能 | 张帅华 | 61 | 1 | Done
|  |  | 注销登录 | 作为一个用户，我希望在游戏里有注销登录的功能，以便我可以快速地退出登陆、更换账号。 | 编写注销登录的界面并实现功能 | 张帅华 | 60 | 1 | Done
6 | 工具 | 作为一个用户，我希望可以有工具功能，以便我可以利用工具拍蚊子、铲屎、收获 | 驱蚊 | 作为一个用户，我希望管理动物时有驱蚊功能，以便可以增加牧场管理的真实感与趣味。 | 编写驱蚊动画效果并实现功能 | 景光赞 | 55 | 1 | Done
|  |  | 铲屎 | 作为一个用户，我希望管理动物时有铲屎功能，以便可以增加牧场管理的真实感与趣味。 | 编写铲屎动画效果并实现功能 | 景光赞 | 53 | 1 | Done
|  |  | 收获 | 作为一个用户，我希望管理动物时有收获功能，以便可以增加管理的成就感。 | 编写收获动画效果并实现功能 | 景光赞 | 50 | 2 | Done
Note on A1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on B1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on C1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable

## 第三次迭代
冲刺号 | 标题 | 用户故事 | 标题 | 用户故事分解 | 任务 | 责任人 | 优先级 | 预估(h) | Status
7 | 活动 | 作为一个运营商，我希望可以有一个活动列表并且通知功能，以便可以让用户查看所有活动并且提醒用户有新的活动 | 签到 | 作为一个运营商，我希望游戏中有签到功能，以便于可以通过福利来吸引用户 | 编写签到布局界面并实现功能 | 张帅华 | 48 | 1 | Done
|  |  | 公告 | 作为一个运营商，我希望游戏中有公告功能，以便于可以向用户玩家推送最新活动及福利消息 | 编写签到公告界面并实现功能 | 张帅华 | 46 | 2 | Done
|  |  | 消息 | 作为一个运营商，我希望游戏中有消息功能，以便于可以通知用户并发放奖励道具等来方便用户使用 | 编写消息布局界面并实现功能 | 张帅华 | 45 | 2 | Done
8 | 答题 | 作为一个运营商，我希望可以有一个答题功能，以便可以让用户通过答题获得饲料，提高学习兴趣。 | 语文题 | 作为一个运营商，我希望在答题系统中有语文题，以便提高用户的语文水平 | 编写语文答题界面，实现获得饲料功能以及后台数据生成 | 杨锡涛 | 42 | 2 | Done
|  |  | 数学题 | 作为一个运营商，我希望在答题系统中有数学题，以便提高用户的数学水平 | 编写数学答题界面，实现获得饲料功能以及后台数据生成 | 杨锡涛 | 41 | 2 | Done
|  |  | 英语题 | 作为一个运营商，我希望在答题系统中有英语题，以便提高用户的英语水平 | 编写英语答题界面，实现获得饲料功能以及后台数据生成 | 杨锡涛 | 40 | 2 | Done
9 | 游戏好友 | 作为一个用户，我希望可以有一个游戏好友功能，以便我可以在游戏里中广泛交友 | 添加好友 | 作为一个用户，我希望在游戏里可以添加好友，以便我可以与好友聊天 | 编写好友界面并实现聊天功能 | 李帅 | 38 | 20 | Done
|  |  | 访问好友牧场 | 作为一个用户，我希望在游戏有访问好友牧场功能，以便我可以帮好友牧场拍蚊子、铲屎等来照看他的动物，增加互动 | 编写访问好友农场功能以及后台管理 | 李帅 | 36 | 5 | Done
|  |  | 查询、删除好友 | 作为一个用户，我希望在游戏有查询、删除好友功能，以便我可以查询和删除对应的好友 | 编写访问查询、删除好友功能以及后台管理 | 李帅 | 35 | 2 | Done
Note on A1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on B1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on C1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable